## Sheet1
Issue No | Issue Description | Issue Raised Date | Issue Resolved Date | Status Of the Issue | Document to be reffered | Programmer | ETC
1 | EF>>Add Contract Issue: Back button is not working. | 2017-11-06 | 2017-11-16 | Fixed
2 | EF>Equipment group>Group Details Issue: When entering “0” in No of Equipment field system is throwing an error “No of equipment is required” instead it should show “No of equipment should be greater than zero” | 2017-11-06 | 2017-11-16 | Fixed
3 | EF>Equipment group>Invoice details Issue: System is showing mandatory errors for Invoice value, TCS % and Description fields instead of only “Description field”. | 2017-11-06 | 2017-11-16 | Fixed
4 | EF>Equipment group>Invoice details Issue: System is showing mandatory errors for Invoice value, TCS % and Tax Amount fields instead of only “Tax Amount”. | 2017-11-06 | 2017-11-16 | Fixed
5 | EF>Equipment group>Invoice details Issue: System is showing mandatory errors for Invoice value and TCS% fields instead of only “TCS%”. | 2017-11-06 | 2017-11-16 | Fixed
6 | EF>Equipment group>Invoice details Issue: System is showing mandatory errors for Invoice value and TCS Amount fields instead of only “TCS Amount”. | 2017-11-06 | 2017-11-16 | Fixed
7 | EF>Equipment group>Invoice details Issue: Toaster message for TCS amount should be changed to “TCS Amount is required” instead of “Tax Amount is required”. | 2017-11-06 | 2017-11-16 | Fixed
8 | EF>Equipment group>Margin Money Issue: Toaster message for Credit period offered field should be changed to “Credit period offered is required” instead of “Select Credit period offered or not”. | 2017-11-06 | 2017-11-16 | Fixed
9 | EF>>Add Equipment group>>Margin Money payments Issue: Margin money payments is not working. | 2017-11-06 | 2017-11-16 | Fixed
10 | EF>Equipment Group>Margin Money. Issue: Clicking TAB button on keyboard is not taking to “save and continue” instead it is giving control to the url. | 2017-11-06 | 2017-11-16 | Fixed
11 | EF>Equipment Group>Group Details. Issue: System is getting hanged when the user is trying to enter 3 digit number in “No of equipment field”. | 2017-11-06 | 2017-11-16 | Fixed
12 | EF>Equipment Group>Margin Money>>Add Payments Hyperlink. Issue: Clicking TAB button on keyboard is not taking to “save and continue” instead it is giving control to the url. | 2017-11-06 | 2017-11-16 | Fixed
13 | EF>Edit Equipment Group>Grid>Details>Equipment Details tab. Issue: System is showing bill of entry, bill of landing number, BoL date for the purchase type “Domestic Intra” | 2017-11-06 | 2017-11-16 | Fixed
14 | EF>>Edit Equipment Group Grid>>Invoice details tab Issue: System is not updating the purchase type, CGST and SGST fields when they are changed from edit mode. | 2017-11-06 | 2017-11-16 | Fixed
15 | Contract grid>>Loan Agreement Issue: Loan Amount field should display Sanctioned Loan Amount whereas it is displaying Discounted LoanAmount. | 2017-11-06 | 2017-11-16 | Fixed
16 | EF>>Contract Details Tab. Issue: Change the below toaster messages. Beneficiary Account Holder Name: Toaster message should be ”Please Enter Beneficiary Account Holder Name .” Beneficiary Account Number: Toaster message should be ”Please Beneficiary Account Number.” | 2017-11-06 | 2017-11-16 | Fixed
17 | EF>>Contract Details> Issue: When selecting preferred payment as Cheque, System is navigating to next tab even though mandatory fields like Bank Account number, Account Holder Name, Bank Branch are not entered. | 2017-11-06 | 2017-11-16 | Fixed
18 | EF>>Contract Details> Issue: When selecting preferred payment as DD, System is navigating to next tab even though mandatory fields like Bank Account number, Account Holder Name, Bank Branch are not entered. | 2017-11-06 | 2017-11-16 | Fixed
19 | EF>>Contract Details> Issue: When selecting preferred payment as NACH, System is navigating to next tab even though mandatory fields like Bank Account number, Account Holder Name, Bank Branch are not entered. | 2017-11-06 | 2017-11-16 | Fixed
20 | EF>> Equipment group>>Loan Amount. Issue: Tab Description should be changed to “Loan details of one equipment can be added from this screen” instead of “You can add details regarding Loan related to this equipment”. | 2017-11-06 | 2017-11-16 | Fixed
21 | EF>> Equipment group>>Loan Amount. Issue: Toaster message of Disbursement Date field should be changed from “Loan Amount Disbursement Date required” to “Disbursement date is required”. | 2017-11-06 | 2017-11-16 | Fixed
22 | EF>> Equipment group>Equipment details>>Upload Documents Issue: After clicking submit button from upload documents page change the toaster message to “Upload Successful” from “File Upload Successfully”. | 2017-11-06 | 2017-11-16 | Fixed
23 | EF>>Contract Grid. Issue: Financier type is not getting updated when the type is changed from manage financiers module. | 2017-11-06 | 2017-11-16 | Fixed
24 | EF>>Margin Money Issue: Deleting the existing payments from MM screen is not updating the Invoice settlement tab accordingly. | 2017-11-06 | 2017-11-16 | Fixed
25 | EF>>Add/Edit Equipment group>>Equipment details tab. Issue: Clicking on previous is removing the data in equipment details tab. | 2017-11-17 | 2017-11-27 | Fixed
26 | EF>>Add/Edit Equipment group>>Margin Money tab. Issue: Margin money payment is throwing an error operation failed. | 2017-11-17 | NA | Fixed
27 | EF>>Add Equipment group>> Equipment details tab. Issue: Doc upload button is disabled in equipment details tab. | 2017-11-17 | 2017-11-27 | Fixed
28 | EF>Contract Grid>Details>Equipment Details tab. Issue: System is showing bill of entry, bill of landing number, BoL date for the purchase type “Domestic Intra". | 2017-11-17 | 2017-11-27 | Fixed
29 | EF>>Edit Equipment group>> Equipment details tab. Issue: When selecting purchase type as imported from invoice details tab system is not changing the Equipment details tab fields according to the purchase type selected. | 2017-11-17 | 2017-11-27 | Fixed
30 | EF>>Contract Details>> Issue: When changing the purchase type data is not getting refreshed. | 2017-11-17 | 2017-11-27 | Fixed
31 | EF>>Edit Equipment group>> Equipment details tab. Issue: Doc upload button is enabled but it is not clickable. | 2017-11-17 | NA | Fixed
32 | EF>>Contract Grid>>Other Details tab. Issue: Financier type is not getting updated when the type is changed from manage financiers module. | 2017-11-17 | 2017-11-27 | Fixed
33 | EF>>Add Contract>>Margin Money Issue: Net margin money payable and total margin money payable fields are not auto calculated. | 2017-11-21 | 2017-11-27 | Fixed
34 | EF>>Add contract>>Equipment Details Issue: When the Invoice no/chassis no is duplicated system is throwing the toaster message and navigating to invoice settlement tab. | 2017-11-21 | 2017-11-27 | Fixed
35 | EF>>Add contract>>Equipment Details Issue: System is checking the duplicate invoice no/chassis no with already existing invoice no/chassis numbers, Duplicate checking in the present tab is not working. | 2017-11-21 | 2017-11-27 | Fixed
36 | EF>> EF>>Add contract>>Equipment Details Issue: Clicking on previous from Invoice settlement tab up to Group details tab and then clicking on save and continue is removing all the data in Equipment Details tab. | 2017-11-21 | 2017-11-30 | Fixed
37 | EF>> EF>>Edit contract>>Equipment Details Issue: Changing the Purchase type from “Domestic intra” to “Imported” system is not updating the Equipment Details tab fields accordingly. | 2017-11-21 | 2017-11-27 | Fixed
38 | EF>> EF>>Add/Edit contract>>Loan Terms Issue: Data in the loan terms tab is not getting saved. | 2017-11-21 | 2017-11-27 | Fixed
39 | EF>>Add contract>>Equipment details tab. Issue: Clicking save and continue from contract details tab and then clicking on previous from equipment details tab is removing the selected branch, internal LAN and type of organization fields from contract details tab. | 2017-11-22 | 2017-11-27 | Fixed
40 | EF>>Add contract>>Contract details tab. Issue: After clicking previous from eqp details tab, when selecting the branch system is showing inter lan as 2 | 2017-11-22 | 2017-11-27 | Fixed
41 | EF>>Add contract>>Invoice details tab. Issue: System is showing Nan in invoice value field when tcs amount in not entered. | 2017-11-22 | 2017-11-27 | Fixed
42 | EF>>Add contract>>Margin Money tab. Issue: Total Margin Money Payable and Due Date for Margin Money fields are not calculated when Discount adjustment type is selected | 2017-11-22 | 2017-11-27 | Fixed
43 | EF>>Add contract>>Margin Money tab. Issue: Payments validation should be on Total Margin money payable not on Total Margin amount. | 2017-11-22 | 2017-11-27 | Fixed
44 | EF>>Add contract>>Equipment group>>Equipment details tab. Issue: Clicking on tab from invoice no field is removing the data in Invoice date and PO date fields. | 2017-11-22 | 2017-11-27 | Open |  | Sharath | 2017-12-05
45 | EF>>Add contract>>Equipment group>>Equipment details tab. Issue: Equipment loan account number field is not showing the account number even after selected same equipment number option from contract details tab. | 2017-11-22 | 2017-11-27 | Fixed
46 | EF>>Add contract>>Equipment group>>Equipment details tab. Issue: Docs reference no field shouldn't be mandatory. | 2017-11-22 | 2017-11-28 | Fixed
47 | EF>>Add contract>>Equipment group>> Invoice settlement tab. Issue: Invoice settlement tab fields are empty. | 2017-11-22 | 2017-11-27 | Fixed
48 | EF>>Add contract>>Equipment group. Issue: Equipment group is not getting added. | 2017-11-22 | 2017-11-27 | Fixed
49 | EF>>Add Contract>> Invoice Details. Issue: For imported and HSS System is throwing BCD error when there is no BCD field in the form, When Pre GST is selected system is throwing GST field error. | 2017-11-28 | 2017-11-29 | Fixed
50 | EF>>Add contract>>Margin Money Payments. Issue: System is throwing multiple errors when the amount is exceeded. | 2017-11-28 | 2017-11-29 | Fixed
51 | EF>>Add contract>>Equipment details. Issue: When purchase type is changed from invoice details tab, previous uploaded docs are not getting refreshed/removed in equipment details tab. | 2017-11-28 | 2017-11-30 | Fixed |  | Sharath | 2017-12-05
52 | EF>>Add contract>>Loan Amount. Issue: When selecting discount adjustment type as “Discount on Margin Money”, Without selecting Credit period offered field in loan amount tab all the corresponding fields for the option Credit period offered Yes are shown. | 2017-11-28 | 2017-11-29 | Fixed
53 | EF>>Add contract>>Invoice details. Issue: “}” symbol is shown in invoice details tab. | 2017-11-28 | 2017-11-29 | Fixed
54 | EF>>Add contact>>Margin Money Issue: Selecting one due date and clicking on save and continue and then clicking on previous is changing the selected date. | 2017-11-28 | 2017-11-29 | Fixed
55 | EF>>Add contact>>Loan Amount Issue: Selecting disbursement date and clicking on save and continue and then clicking on previous is changing the date format. | 2017-11-28 | 2017-11-29 | Fixed
56 | EF>>Add Contract>>Equipment group grid>>Equipment details tab>>docs view pop up Issue: List of documents view is wrong. | 2017-11-28 | 2017-11-30 | Fixed |  | Sharath | 2017-12-05
57 | EF>>Add Contract>>Equipment group grid>>Equipment details tab Issue: Document name shown is wrong in the document name field of docs view popup. | 2017-11-28 | 2017-11-30 | Fixed
58 | EF>>Add/Edit contract>>Loan Terms, Moratorium. Issue: Data saved successfully toaster message is not shown for Loan Terms & Moratorium tabs. | 2017-11-28 | 2017-11-29 | Fixed
59 | EF>>Contract grid>>Interest rate tab. Issue: Click to submit is not working while logging revise rate of interest. | 2017-11-28 | NA | In Progress |  | Pramod
60 | EF>>Contract grid>>Fees tab. Issue: Log fees pop up is throwing an error and the user is unable to log new fees. | 2017-11-28 | 2017-11-29 | Fixed
61 | EF>>Contract grid>>Fees tab. Issue: 1) Log fees pop up “Type” field doesn’t contain penal interest and other as options. 2) Total paid is not auto calculated. | 2017-11-28 | 2017-11-30 | Fixed
62 | EF>>Contract grid>>Fees tab. Issue: Branch is not displayed in other details tab. | 2017-11-28 | 2017-11-30 | Fixed
63 | EF>>Edit Contract>>Contract details tab. Issue: Branch field is empty in edit mode. | 2017-11-28 | 2017-11-30 | Fixed
64 | EF>>Edit Contract>>Margin money payments. Issue: After clicking payments hyperlink time is not removed in date fields and clicking on submit is throwing an error “Operation failed”. | 2017-11-28 | 2017-11-30 | Fixed
65 | EF>>Edit Contract>>Invoice settlement tab. Issue: Credit discount amount and outstanding amount fields are not updated in edit mode. | 2017-11-28 | NA | Fixed | 73 | Sharath | 2017-12-05
66 | EF>>Add/Edit contract>>Equipment group grid>>Margin Money tab. Issue: Margin Money tab is not updated according to the changes made. | 2017-11-28 | 2017-11-30 | Open |  | Sharath | 2017-12-05
67 | EF>>Edit contract>>Equipment group >>Equipment details tab. Issue: All the check boxes are unchecked in edit mode. | 2017-11-28 | NA | Fixed
68 | EF>>Edit contract>>Equipment group grid and Equipment details >>Equipment details tab. Issue: BoE and BoL date fields are duplicated in edit mode. | 2017-11-28 | 2017-11-30 | Fixed
69 | EF>>Edit Contract>>Loan Terms Tab. Issue: Discounted loan amount is not getting updated when the user has made changes in the contract. | 2017-11-28 | NA | Fixed |  | Pramod | 2017-12-05
70 | EF>>Add/Edit Contract>>Margin Money Payments. Issue: When adding second payment system is throwing error “Operation Failed” as the date format is wrong. | 2017-11-30 | 2017-11-30 | Fixed
71 | EF>>Add contract>>Equipment details tab. Issue: Docs are not getting uploaded. | 2017-11-30 | 2017-11-30 | Fixed
72 | EF>> Add contract>> Equipment details tab. Issue: Clicking on submit without entering any data on upload doc modal popup is throwing some random toaster message, Field without data should be highlighted in red. | 2017-11-30 | 2017-11-30 | Fixed
70 | EF>>Add contract>>Margin Money Payments. Issue: When the account number is more than 10 digits for the payment type RTGS system is throwing an error “Operation Failed.” | 2017-12-01 | NA | Fixed | Pending Issues 1 Dec
71 | EF>>Add contract>>Equipment group. Issue: When the loan amount is large value system is not showing utilized loan in the equipment group. | 2017-12-01 | NA | Fixed | Pending Issues 1 Dec
72 | EF>>Contract Grid>>Fees tab. Issue: Penal interest tab is added and clicking on it is showing fees tab details. | 2017-12-01 | NA | Fixed | Pending Issues 1 Dec
73 | EF>>Edit Contract>>Margin Money payments. Issue: After deleting the existing payments system is not changing the invoice settlement tab accordingly. | 2017-12-01 | NA | Fixed | Pending Issues 1 Dec | Sharath | 2017-12-05
74 | EF>>Edit Contract>>Margin Money payments. Issue: System is accepting zero in the amount field instead system should throw an error “Amount should be greater than zero”. | 2017-12-01 | NA | Fixed | Pending Issues 1 Dec
75 | EF>>Equipment grid>>Invoice details tab Issue: BCD, IGST, Cess fields are not shown in invoice details for HSS and Imported purchase types(BCD, IGST, Cess fields are there in contract grid but not in equipment grid) | 2017-12-01 | NA | Open | Pending Issues 1 Dec
76 | EF>>Add/Edit Contract>>Invoice Settlement tab Issue: When selecting Invoice details tab from Invoice Settlement tab system is selecting the tab heading of both the tabs. | 2017-12-01 | NA | Fixed | Pending Issues 1 Dec
77 | EF>>Equipment group grid>>Margin Money. Issue: Line below Discount amount field is not proper. | 2017-12-07 | NA | Open | Pending Issues 7 Dec
78 | EF>> Contract Grid. Issue: Deleting contract and clicking on browser back button is throwing am error. | 2017-12-07 | NA | Open | Pending Issues 7 Dec
79 | EF>>Contract grid. Issue: Foreclosing a equipment and clicking on edit equipment group is throwing an error. | 2017-12-07 | NA | Open | Pending Issues 7 Dec
80 | EF>>Contract Grid. Issue: Loan Amount shown is wrong. | 2017-12-07 | NA | Open | Pending Issues 7 Dec
81 | EF>>Edit contract>>Contract details. Issue: Type of organization field is not getting updated when it is changed from manage financiers tab. | 2017-12-07 | NA | Open | Pending Issues 7 Dec
82 | EF>>Edit Contract>>Equipment details Issue: Docs are not getting removed in edit mode when the purchase type is changed from invoice details tab. | 2017-12-07 | NA | Open | Pending Issues 7 Dec